## Sheet1
[6 empty] | Team Members | [9 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[6 empty] | First Name | Last Name | Nickname (max 6 characters)
[6 empty] | Emily | Sookwa | ES
[6 empty] | Maryam | Tehranizadeh | MT
[6 empty] | Maliheh | Zarei Chitgar | MZ
Add more rows as necessary
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| ES | MT | MZ | 0 | 0 |  |  |  |  | ES | MT | MZ | 0 | 0
Milestone 1
2023-02-01 | [8 empty] | Define project scope and objectives: | 30 | 30 | 30 | 0 | 0 |  | Project scope:
2023-02-01 | [8 empty] | 3 opportunity statements. Rank. Write mission statement | 40 | 40 | 40 | 0 | 0 |  | 1-The bike rental app will allow users to search for and rent bikes from a network of bike rental locations. | Three opportunity statements for bike rental app
2023-02-03 | I |  |  |  |  | Define project scope and objectives | 2 | To establish clear project goals and objectives for the bike app development process. | Total hours | 70 | 70 | 70 | 0 | 0 |  | 2-Users will be able to select from a variety of bike types, rental durations, and pickup/drop-off locations. | 1. To leverage technology to provide a convenient and efficient bike rental experience for users.
2023-02-03 |  | I |  |  |  | Research best practices and competitor analysis | 2 | To gather information on industry standards and what competitors are doing, so that the project team can make informed decisions and create a competitive product. | [7 empty] | 3-The app will include features for users to make payments, view their rental history, and receive support from the rental company. | 2. To create a sustainable and environmentally-friendly transportation option for individuals and communities.
2023-10-04 |  |  | I |  |  | Create project timeline, including milestones and deadlines | 2 | To ensure that the project is completed on time and within budget. | [7 empty] | 4-The app will have a backend management system for the rental company to manage bike inventory, monitor rentals, and view revenue reports. | 3. To generate new revenue streams for the bike rental company through the expansion of their services into the digital space.
2023-10-04 | I |  |  |  |  | Define user requirements and gather feedback from stakeholders | 1 | To understand the needs and preferences of the target audience and incorporate them into the development process. | [7 empty] | Objectives: | In terms of ranking, it depends on the specific priorities of the project. However, one possible way to rank these opportunity statements is as follows:
2023-10-04 |  | I |  |  |  | Conduct market research and identify target audience | 1 | To gain a better understanding of the target audience and inform the development process. | [7 empty] | 1-To provide a convenient and accessible way for users to rent bikes for leisure or transportation purposes. | 1. To leverage technology to provide a convenient and efficient bike rental experience for users.
2023-10-05 | [5 empty] | Create project budget, including resources and cost estimates | 1 | To ensure that the project is completed within budget and resources are allocated effectively. | Total team hours | [5 empty] | 210 | 2-To increase the efficiency of bike rental operations for the rental company. | 2. To generate new revenue streams for the bike rental company through the expansion of their services into the digital space.
2023-10-05 |  |  | I |  |  | Develop project charter and presentation deck for project review and approval | 1 | To establish clear project goals, objectives, and expectations for all stakeholders. | [7 empty] | 3-To create a user-friendly and intuitive app that is easy to use. | 3. To create a sustainable and environmentally-friendly transportation option for individuals and communities.
2023-10-05 |  | I |  |  |  | Create project risk register and contingency plan | 1 | To establish a clear understanding of what resources and funds will be needed for the project, so that the team can ensure it stays on budget and allocate resources effectively. | [7 empty] | 4-To integrate payment processing securely into the app to facilitate transactions. | Mission statement: Our mission is to provide a convenient, efficient, and sustainable bike rental experience through technology. By making bike rental accessible and easy to use, we aim to reduce the barriers to environmentally-friendly transportation and generate new revenue for our company.
2023-10-06 |  |  | I |  |  | Conduct team building activities and establish project communication plan | 1 | To build strong relationships and teamwork among the project team, and to establish clear and effective communication channels to ensure everyone is on the same page and working together effectively. | [7 empty] | 5-To gather data on rental trends and user behavior to inform future business decisions.
2023-10-06 | I |  |  |  |  | Gather information on current trends and advancements in bike app technology | 1 | To understand the latest advancements and trends in bike app technology, so that the project team can stay up-to-date and create a cutting-edge product.
2023-10-07 |  | I |  |  |  | Conduct competitor analysis and identify key features and user experiences offered by top bike apps | 2 | To gather information on what competitors are offering and what features and experiences users are looking for, so that the project team can create a competitive product that meets the needs of its target audience.
2023-10-07 |  |  | I |  |  | Research user behavior patterns and preferences in relation to bike app usage | 2 | To understand the behavior patterns and preferences of bike app users, so that the project team can create a product that is intuitive and appealing to its target audience.
2023-10-07 | I |  |  |  |  | Conduct user interviews and surveys to gather insights and feedback on desired features and functionality | 1 | To gather feedback and insights from users, so that the project team can create a product that meets their needs and exceeds their expectations.
2023-10-08 |  | I |  |  |  | Analyze market needs and identify unmet needs in the bike app space | 1 | To understand the current market needs and identify areas where the bike app being developed can offer unique and innovative solutions.
2023-10-09 |  |  | I |  |  | Review case studies and success stories from other bike apps to gather best practices and lessons learned | 2 | To learn from the experiences and successes of other bike apps in order to improve the development of the bike app being created. Objective: To research and analyze case studies and success stories to identify best practices, lessons learned, and opportunities for improvement.
2023-10-09 | I |  |  |  |  | Analyze user data to identify key pain points and areas for improvement in existing bike apps | 1 | To understand the current pain points and areas of improvement of existing bike apps to create a better user experience for the app being developed.
2023-10-09 |  | I |  |  |  | Evaluate existing technology and tools available for bike app development and recommend potential solutions | 2 | To identify the best technology and tools for developing the bike app and ensure that the final product is of high quality and user-friendly.
2023-02-10 |  |  | I |  |  | Create a report summarizing research findings, including key insights and recommendations for the bike app development process | 1 | To create a comprehensive report that summarizes the research findings, key insights, and recommendations for the development process, to be used as a reference and guide for the project.
Milestone 2 |  | I |  |  |  | I interviewd by one of our customers ,recorded, created file | 8 | To create a comprehensive report that summarizes the research findings, key insights, and recommendations for the development process, to be used as a reference and guide for the project.
2019-01-25 | 1 |  |  |  |  | work at home | 3 | Create draft interview script | Draft interview script | 5 | 5 | 5 | 0 | 0
2023-02-11 |  | I |  |  |  | Create database , analyzed fields in each tables, made relationship between tables | 8 | For create table first of all I undrestnd project and then listed all requirements that need in project, and then anylyzed tables and fields and relatinship between them | 8 | 5 | 5 | 5 | 0 | 0
2023-02-12 |  | I |  |  |  | Created register form, login form | 8 | For my team member created register and login form , | Total team hours | 5 | 5 | 5 |  |  | 15
2023-02-12 |  | I |  |  |  | Created sever part | 20 | For server I watched some video and try to created server parts
2023-02-13 | I | I |  |  |  | Created Navbar | 9 | For Navbar I watched some videos to help me how can create Navbar with bootstrap
2023-02-14 | 1 | 1 | 1 | 1 | 1 | Meet | 3 | Plan sprint 1 | Sprint 1 goal. Sprint backlog | 15 | 15 | 15 | 3 | 3
2023-02-15
2023-02-15 |  | I |  |  |  | Solved my repository problem | 8 |  | Total hours | 15 | 15 | 15 | 3 | 3
2023-02-16 | I |  |  |  |  | Created UML doagrams | 10 | For creating sequence diagram I searched and google about visio then I made it | Total team hours | [5 empty] | 51
2023-02-17 |  | I |  |  |  | Update my database ,created tbl_login, created relationship between tables and tbl_login | 10 | I deleted relationship between tables and tbl_user and then I deleted tbl_users
Sprint 2 2023-02-17 | I |  |  |  |  | Created sprint 2 | 10 | I added tbl_login, insertet data on it, made relation ship between it and other tables
2019-01-25 |  | 1 |  |  |  | Work in lab | 5 | Integrate motion sensor into project | Sensor data makes its way to serer and then to phone | 10 | 10 | 10 | 0 | 0
2023-02-18 |  | I |  |  |  | Search about algorithm for creating safe and secure payment rent bike | 5 |  | Total hours | 10 | 10 | 10 | 0 | 0
2023-02-18 |  | I |  |  |  | Created and oronized all documents for presentation,created blog,product baklog, sprint1,sprint2,sprint3 |  |  | Total Team hours | [5 empty] | 30
Sprint 3 |  | I
2019-01-25 | 1 | 1 | 1 | 1 | 1 | Prepare final demo | 2 | List all functionality to be demoed: What order to demo it? How to best demo each function? | Final Demo 10 minutes long | 2 | 2 | 2 | 2 | 2
[9 empty] | Total hours | 2 | 2 | 2 | 2 | 2
[9 empty] | total team hours | [5 empty] | 10
[9 empty] | Total hour over project | 102 | 102 | 102 | 5 | 5
[9 empty] | Total team hours over project | [5 empty] | 316