## Cover Page
<Product Name>
Prepared By:
Team X
<Team Member>: <Student Id>
<Team Member>: <Student Id>
<Team Member>: <Student Id>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | 6 | Sprint | Status | Conversation | Confirmation
BK-1 | Functionality | As a customer I would lilke to login in rental bike application. | 3 | Sprint 1 | In Progress | This is the basic login screen that user enter username and password | 1. User can login after putting proper credentials 2.Screen disply message to custmer if username or passwors is not correct
BK-2 | Functionality | As a customer I would like see all rent Bike location in application | 4 | Sprint 1 | In Progress | This will allow the customer to select see all locations can rent Bike | 1. Customer can see all locations about Bixi Bike 1. Customer could select which locations is close to rent Bike
BK-2-1 | List bikes available | As a customer I would like to know how many bike are availble in each location , I need to see photo for bike and rent cost | 4 | Sprint 1 | In Progress | This will allow customer knows how many bikes are available at location | 1- Customer can see how many bikes are availeble in real time
BK-2-2 | Real time bike avaiablity | As a customer I would like the real-time bike availability | 4 | Sprint 1 | In Progress | This will allow the customer see which bikes available in real time | 1- Customer can see quickly and easily find a bike to rent
BK-3 | Reserve bike | As a customer I would like reserve selected bike | 4 | Sprint 1 | In Progress | This will allow customer reserve selected bike and help customer to reserve bike and then rent it | 1. Customer can reserve bike in specific location
BK-4 | Payment | As a customer I would l like to new payment option | 5 | Sprint 1 | Sprint 2 | This will allow the customer to pay cost for selected bike | 1.Customer can pay the payment with this form without this page customer has dificalty for pay the cost
BK-5 | History payment | As a customer I would like to see history payment | 5 | Sprint 1 | In Progress | This will allow customer to see all history about payments | 1. Customer can see all history about own payments this is usefulf for customer to see own payments history
BK-6 | Cancle reservation | As a customer I would like to cancle my reservation | 4 | Sprint 1 | In Progress | This will help customer to cancle reservation without phone call | 1- Customer can cancle Bike reservation without need to phone call and speak with customer service
BK-7 | check statud maintainance bike | As a customer I want to see status my maintainance bike | 4 | Sprint 1 | Not in sprint | This will help customer know better tracking and maintenance of bikes to ensure they are in good condition and available for rent at all time | 1- Customer can track and know status about bikes in any locations 2- this option can help customer to know real status about any bikes in location to manage time and make deision about rent it
BK-8 | secure payment | As a customer I want this app have secure payment option | 12 | Sprint 2 | Completed | We have to search how can create safe and secure application | 1- customer can click on payment button then shows banks list then can login on bank site
BK-9 | Show confirmation payment | As a customer I want this app show me confirmation message after payment | 8 | Sprint 2 | Completed | This wil alow custmer to know payment is done | 1- After finish the payment process shows message to custmer to let them know is done
BK-10 | show which bikes are available | As a custmer I want to show me what typse of bike are available | 6 | Sprint 2 | Completed | in this page shows customer which biks are available | 1- Show which bike is available so customer can select the best bike
Bk-11 | shows which biks in location | As a customer I want shows me in specific location and specific time which bik is available | 8 | Sprint 2 | Completed | We decided our app has facility to show customers in specific location which bike whill be available, also customer can modify reservation or cancle it.
B-12 | Show all history reservation | As a custmer I want to see all personal information ,all history about my reservationsand my payments and then can update my reservation and also my personal information | 10 | Sprint 3 | Completed | We decided this app can facility to customer can see and update personal information and also can delete or update bike reservation | 1- show all personal information, all reservations, all payments , also they have can change their personal information and delete reservations
B-13 | Price | As a cusomer I need to know how much will be price
B-14 | Mobile app | As a customer I want this app install in cellphone | 12 | Sprint 3 | On Hold | We decide this app can install in mobile this help customer can work with this app any where | 1-We have planned creat application that be install in mobile , it helps customer in any place can change and see , tracking reservation
B-15 | status about bike maintainance | As a custmer I need to undrestand status about bike maintainance | 15 | Sprint 3 | On Hold | we decide this app has page that shows customer status about bikes and status about maintainance | 1- After custmer entered bike id , that can see bike status about maintainance

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
BK-1 | BK-1.1 | Create Register and login form and develop | Creat register and login UI form so customer can have register and then login in Rental Bike application, Develop user registration functionality that allows users to create an account with their personal information and payment details | 10 hrs | Planned | We create register and login UI form, this form has validation if user enter wrong username and password shows error message
BK-2 | BK-2-1 |  | Createpage that shows all locations for rent bikes, | 5hrs | In Progress | We create page that show custmer, list bike's location
BK-2-1 | BK-2.1 | Bike Listing Page | Create a page that displays the available bikes for rent in specific location , including their pictures, descriptions, and rental cost | 8 hrs | In Progress | We create facility with create button on form when customer click on it can show all bikes's location
BK-2-2 | bk-2-2 | Availe real time bike | Create option that shows customer when the bike is available | 3hrs | In Progress | We put option to shows customer when the bike is available
BK-3 | BK-3 | Booking Form | Build a form that allows customer to select the bike that they want to rent and specify the rental dates, and displays the total cost of the rental | 8hrs | In Progress | we decide have this form that customer can select bike in specific location in specific dates, also we need to show cost for rent bixi bike
BK-4 | BK-4 | Payment form | Build a form that allow customer to payment for renting bike | 8hrs | On Hold | We need to search more about payment gateway and seach about algorithm to make website safe for customer
BK-5 | BK-5 | Rental History | Create a page where users can view their rental history, including the bikes they rented and the rental dates and costs | 8hrs | Planned | we decide have this option that customer can do payment safe and easily with this app.we should more search about app security
BK-6 | BK-6 | Cancle reservation | Create a form that customer can cancle bike reservation | 5hrs |  | we decide to set option if customer want to cancel their reservation
BK-7 | BK-7 | tracking maintainance bike | Create a form that customer can see and track real status about bike maintainance | 5hrs | Planned | We decided our application has form to show tracking status about bike maintainance

## Sprint 2
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
BK-8 | BK-8.1 | Implement Payment Gateway | Research and implement a secure payment gateway for the rental bike application. Ensure that the payment gateway complies with industry standards for secure online transactions. | 12hrs | Planned | We searched into how we could make Ensure that the payment gateway complies with industry standards for secure online transactions.
BK-9 | BK-9.1 | Implement Rental Confirmation | Develop a rental confirmation page that confirms the customer's rental information, rental dates, rental duration, rental cost, and other details. Also, send a confirmation email to the customer's email address | 8 hrs | Planned | we develop rental form in application , in this page customer can see all informationabout rent bike inslude bike cost,rent date and ..
BK-10 | BK-10.1 | Integrate Bike Availability | Integrate bike availability into the rental booking process, allowing customers to select available bikes and reserve them. | 6 hrs | In Progress | We create form that shows customer in specific location which bikes are availabe , it helps customer to select good bike
BK-11 | BK-11.1 | Develop Bike Reservation System | Develop a system that allows customers to reserve a bike for a specific time and location. Also, allow them to cancel or modify reservations if necessary. | 8 hrs | In Progress | We create reservation form to make facility for customer then customer can select bike and reserve it , then they can take it

## Sprint 3
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
BK-12 | BK-12.1 | Enhance User Profiles | Enhance user profiles to allow customers to view and edit their personal information, payment details, and rental history | 10 hrs | Planned | We created good forms to help customers can tracking history payment, we created option that custmers can edit all personal information data
BK-13 | BK-13.1 | Implement Location-based Pricing | Implement a pricing system that varies based on the location of the bike rental. Consider implementing dynamic pricing that adjusts rental prices based on demand. | 12 hrs | Planned | We created option to change cost for rent acording to rush hour changed
BK-14 | BK-14.1 | Develop Mobile Application | Develop a mobile application that allows customers to rent bikes from their smartphones. The app should include all the functionality of the web application, including bike availability, rental booking, payment processing, and rental history | 20 hrs | Planned | We created facility that our app can intall in mobile
BK-15 | BK-15.1 | Implement Bike Maintenance Schedule | Develop a system that tracks the maintenance schedule for each bike, including routine maintenance and repairs. Also, develop a system for alerting maintenance staff when a bike requires maintenance or repair | 10 hrs | Planned | We created mobile app to have possibilities for alert mainatinace repair